## Overview
Field | Value
Title | Requirements traceability matrix — CarePath 1.0
Document | TST-CAREPATH-003
Version | 1.0.0
Status | Current as of build 1.0.0
Owner | QA Lead
Suite result | 111 passed, 0 failed
Line coverage | 91% (floor 85%, NFR-13)
Notice | Demonstration artifact. Synthetic content only - not a clinical record.

## Narrative
Section | Text
Requirements traceability matrix — CarePath 1.0 | Reviewed at each release. A requirement with no covering test is a release blocker unless it appears in the uncovered table with an owner.
Non-functional requirements | Legend: ✓ covered by the suite · ◐ partially covered · ✗ verified outside the suite, or not at all
Findings raised by this review | Recorded here rather than left implied by a ◐.

## 1. Business requirements
BR | Realised by | Verified by
BR-01 One record per person | FR-01, FR-02 | TestMedicalRecordNumbers, TestRegistration::test_a_duplicate_number_is_a_conflict
BR-02 Referrals tracked end to end | FR-07, FR-08 | TestTransitions::test_the_whole_happy_path_can_be_walked
BR-03 Prioritised outreach | FR-06 | TestScoring::test_every_contributing_factor_is_named
BR-04 Access report on demand | FR-11 | TestAuditEndpoint::test_an_auditor_reads_the_trail_for_a_patient
BR-05 Consent honoured before disclosure | FR-09, FR-10 | Partially covered — see below
BR-06 Standard exchange format | FR-10 | TestBundle::test_a_bundle_holds_the_patient_and_everything_recorded

## 2. Functional requirements
FR | Requirement | Code | Tests
FR-01 | Register a patient | services/patients.py::register, domain/identifiers.py::valid_mrn | TestMedicalRecordNumbers (8), TestRegistration (4), TestApi::test_a_patient_can_be_registered_and_read_back, ::test_a_duplicate_registration_is_a_409, ::test_a_malformed_number_is_a_422
FR-02 | Read a patient | services/patients.py::read | TestRetrieval::test_an_unknown_patient_is_not_found, ::test_reading_writes_an_audit_event_carrying_the_purpose, TestApi::test_an_unknown_patient_is_a_404
FR-03 | Search by family name | services/patients.py::search | TestRetrieval::test_a_search_records_what_was_looked_for_not_what_was_found, ::test_a_search_matches_on_a_prefix_only
FR-04 | Record an encounter | services/encounters.py::open_encounter | TestOpeningAnEncounter (5)
FR-05 | Record an observation | services/encounters.py::add_observation | TestObservations (3)
FR-06 | Readmission risk | domain/risk.py, services/risk.py | TestAge (3), TestObservationRanges (5), TestScoring (5), TestStayLength (2), TestService (2), TestApi (3)
FR-07 | Create a referral | services/referrals.py::create | TestCreating (3)
FR-08 | Referral lifecycle | domain/referral_state.py, services/referrals.py::transition | TestLifecycleMap (11), TestTransitions (4), TestApi::test_a_forbidden_move_is_a_409
FR-09 | Consent | services/consent.py | TestRecording (2), TestCurrentPosition (4), TestApi (3)
FR-10 | FHIR export | fhir.py, api/routes_fhir.py | TestResources (4), TestBundle (1), TestApi (3)
FR-11 | Audit every access | security/audit.py | test_registering_writes_an_audit_event, test_reading_writes_an_audit_event_carrying_the_purpose, test_opening_an_encounter_writes_an_audit_event, TestAuditEndpoint (3)
FR-12 | Health endpoints | api/routes_health.py | TestHealth (3)

## 3. Non-functional requireme
NFR | Covered | By what
NFR-01 availability | ✗ | Synthetic probe and monthly SLO report — Platform
NFR-02 latency | ✗ | Manual load test before release — QA Lead
NFR-03 audit in the same transaction | ◐ | The audit rows are asserted per endpoint. That they share the transaction is verified by code review, not by a test that rolls one back
NFR-04 no PHI in logs | ◐ | TestRedaction (5) covers the redaction function. Whether each log call passes PHI to it is not covered — see the finding below
NFR-05 authn and authz | ✓ | TestAuthentication (5), TestAuthorisation (5), plus a role-refusal test on every router
NFR-06 bounded queries | ◐ | TestBounds (2) covers encounters. Patient search is not covered — see the finding below
NFR-07 file-mounted secrets | ✗ | Deployment review — Platform
NFR-08 correlation identifier | ✓ | test_every_response_carries_a_correlation_identifier, test_a_supplied_correlation_identifier_is_echoed
NFR-09 audit immutability | ✗ | Code review and database grants — Security Architect
NFR-10 graceful degradation | ◐ | The degraded flag is asserted present. The degraded path is verified by fault injection in the soak, not by a test
NFR-11 transaction ceiling | ✗ | Slow-query log — Platform
NFR-12 rate limiting | ✗ | Not implemented. See the risk register
NFR-13 coverage and traceability | ✓ | This document; coverage gate in the pipeline
NFR-14 runs with no configuration | ✓ | conftest.py starts the service with a database path and nothing else

## 4. Regulatory requirements
REG | Verified by
REG-01 audit controls | FR-11 tests, plus the read-only audit router
REG-02 unique user identification | test_registering_writes_an_audit_event asserts the actor is the principal's subject
REG-03 minimum necessary | TestAuthorisation (5); test_an_unknown_patient_is_a_404 pins that absence and refusal are indistinguishable
REG-04 transmission security | Ingress configuration — Platform
REG-05 encryption at rest | Volume configuration — Platform. Gap G-02
REG-06 consent and lawful basis | FR-09 tests. Gap G-03
REG-07 FHIR R4 | TestResources (4), TestBundle (1). Gap G-04: no automated validator
REG-08 erasure and portability | Portability by FR-10. Erasure is manual — gap G-01

## 5. Findings raised by this
# | Requirement | Finding | Severity | Owner
T-01 | NFR-06 | GET /patients declares limit with no le bound, unlike the encounter, referral and consent listings. There is no test asserting an upper bound on patient search | High | Engineering
T-02 | NFR-04 | No test asserts that a given log call is free of PHI. The redaction function only catches shaped identifiers; a patient name passes through it unchanged | High | Engineering
T-03 | BR-05 | No test asserts that the FHIR export consults consent. The consent service is fully tested; nothing joins it to the export path | High | Engineering
T-04 | NFR-03 | The referral status transition has no audit assertion, unlike every other write in the suite | Medium | Engineering
T-05 | NFR-12 | Nothing to test — the control does not exist. Coverage cannot show this, because uncovered code that was never written does not appear in a coverage report | Medium | Engineering