## Slide 1
CarePath 1.0.0 — release readiness review
Clinical Systems Board · 2026-06-02
Demonstration artifact — synthetic content only, not a clinical record.

## Slide 2
Purpose
• Decide whether CarePath 1.0.0 releases to the pilot on 4 June
• Pilot scope: 400 patients, two clinics, behind an IP allow-list
• Audit remediation commitment (C-04) falls due 30 June
Notes: The remediation date is the pressure in the room. Everyone knows it and nobody says it out loud.

## Slide 3
Quality gates
Gate | Target | Actual | Verdict
Tests passing | all | 111 / 111 | Pass
Line coverage | 85% | 91% | Pass
Lint | clean | clean | Pass
FRs with a test | 12 / 12 | 12 / 12 | Pass
Sev 1-2 defects open | 0 | 0 | Pass
High-severity findings open | 0 | 3 | FAIL
Notes: Five green rows and one red one. The five are quantitative and the red one is not, which is roughly how it was read.
Full table has 6 rows; 6 shown.

## Slide 4
Open findings
Ref | Finding | Severity
T-01 | Patient search accepts an unbounded limit | High
T-02 | Patient name written to the application log | High
T-03 | Export does not consult consent before disclosure | High
Notes: Three findings, presented on one slide, discussed as one item. T-03 is the only one that defeats a business requirement rather than a non-functional one. Nothing on this slide says so.
Full table has 3 rows; 3 shown.

## Slide 5
Recommendation
• Release to pilot with waiver W-01 covering all three findings
• Exposure is bounded: 400 patients, two clinics, IP allow-list
• All three scheduled for 1.0.1
• Waiver expires at general availability
Notes: One rationale for three findings. It addresses exposure - who can reach the service - and not blast radius, which is what one authorised user can do once they are inside. T-01 became INC-2026-0814 ten weeks later for exactly that reason.

## Slide 6
Decision
• Approved: release to pilot on 2026-06-04 under waiver W-01
• Proposed: Delivery Manager · Seconded: Clinical Director
• No objections recorded
• Actions: none raised
Notes: The minute records no discussion of T-03 specifically. This slide is the whole governance failure, in four bullets, approved by people doing their jobs properly with the information in front of them.