## Overview
Field | Value
Title | Risk register — CarePath
Document | GOV-CAREPATH-002
Version | 1.4
Status | Active
Owner | Delivery Manager
Last reviewed | 2026-08-19, after INC-2026-0814
Notice | Demonstration artifact. Synthetic content only - not a clinical record.

## Narrative
Section | Text
Risk register — CarePath | Scoring: likelihood × impact, each 1–5. Score 15 or above is escalated to the Clinical Systems Board.
Escalated to the board | R-01, R-02, R-05 and R-10, tabled for 2026-09-02.
Escalated to the board | R-10 is the one to take first. The other three were each visible before release — R-01 as T-03, R-02 as T-04, R-05 as NFR-12 — and each was carried past the gate that existed to catch it. R-10 is the reason why, and fixing the individual findings without fixing it leaves the mechanism in place for the next release.

## 1. Risk register CarePath
ID | Risk | L | I | Score | Treatment | Owner | Status
R-01 | A record is disclosed to a partner for a patient who withdrew consent, because the export path does not consult the consent record | 4 | 5 | 20 | Mitigate — implement the check in 1.0.1. Interim: manual confirmation by the requester, which is not a control | Engineering | Open, escalated
R-02 | An access to a patient record is not recorded, so an access report is incomplete when produced under audit | 3 | 5 | 15 | Mitigate — audit the referral transition (T-04); redesign the reconciliation so an unaudited path is detectable | Engineering | Open, escalated
R-03 | Patient names in application logs reach the aggregator, where retention and access differ from the clinical record | 4 | 3 | 12 | Mitigate — remove the identifying fields from the scoring log line (T-02); sprint log sampling | Engineering | Open
R-04 | An unbounded query degrades or halts the service | 2 | 4 | 8 | Realised as INC-2026-0814. Actions A-1, A-2 open | Engineering | Realised, actions open
R-05 | Credential stuffing against the token endpoint succeeds, because there is no rate limiting and tokens do not expire | 3 | 5 | 15 | Mitigate — implement NFR-12 in 1.1. Interim: IP allow-list | Engineering | Open, escalated
R-06 | A database administrator reads patient rows directly | 2 | 4 | 8 | Accept for 1.0 (G-02); administrative sessions logged and reviewed monthly | Platform | Accepted
R-07 | An erasure request cannot be served within the statutory period because the procedure is manual | 2 | 4 | 8 | Accept for 1.0 (G-01); two named engineers under change control | Information Governance | Accepted
R-08 | Northvale cannot ingest the export | 1 | 3 | 3 | Closed — confirmed 2026-03-09, A-02 discharged | Integration Lead | Closed
R-09 | Coordinators do not act on the risk list, so BR-03 delivers nothing | 3 | 4 | 12 | Monitor — the explainability decision in ADR-0003 is the mitigation; measured at the pilot review | Product Owner | Monitoring
R-10 | A waiver bundles several findings, so the weakest rationale carries the strongest finding | 4 | 4 | 16 | Realised — W-01 bundled T-01, T-02 and T-03. Actions A-3, A-4, A-5 open | Delivery Manager | Realised, escalated
R-11 | An operational procedure is followed confidently from a document that no longer matches the deployment | 3 | 3 | 9 | Mitigate — runbook review at each release; currently overdue | Platform | Open
R-12 | The risk score is read as clinical advice, voiding the REG-05 non-applicability determination | 2 | 5 | 10 | Mitigate — wording in the API description, release notes and coordinator training; reviewed if scoring changes | Clinical Lead | Monitoring